# Financial Due Diligence Memo

ATOMiK  ·  State-Aware Compute Architecture  ·  Pre-Seed  ·  May 2026

Last updated: 2026-05-27

Purpose: founder-prepared financial diligence memo for Friday investor discussion, pending CFO/counsel review. This is not legal, tax, accounting, or securities advice. It is a founder-ready diligence memo to keep the financing story coherent if a fractional CFO is unavailable.

# Bottom Line

The $2.0M target pre-seed is defensible as a milestone-based proof round, not as a chip-production round. The fundable financial story is:

$2.0M buys 18 months to convert hardware-backed primitive proof into measured workload proof, counsel-reviewed IP readiness, ASIC feasibility, and design-partner/licensing diligence. It does not fund tape-out.

The main diligence risk is not the ask amount. The main risk is making the round sound more mature than it is. ATOMiK should not present a valuation cap, revenue forecast, customer traction, production-silicon budget, or downstream savings model unless the supporting work is complete.

# Math Checked

## Use Of Funds

Target plan totals to $2.0M:

| Category | Amount | Percent |
| --- | --- | --- |
| Engineering and demo hardening | $600K | 30.0% |
| Customer proof | $400K | 20.0% |
| IP and legal | $300K | 15.0% |
| ASIC feasibility | $300K | 15.0% |
| Finance, GTM, and ops | $250K | 12.5% |
| Reserve | $150K | 7.5% |
| Total | $2.0M | 100.0% |

Minimum plan totals to $1.25M. Stretch plan totals to $2.75M.

## Runway Arithmetic

| Scenario | Raise | Reserve | Spendable cash | Planning runway | Gross monthly budget | Ex-reserve monthly budget |
| --- | --- | --- | --- | --- | --- | --- |
| Minimum | $1.25M | $100K | $1.15M | 12 months | ~$104K/mo | ~$96K/mo |
| Target | $2.0M | $150K | $1.85M | 18 months | ~$111K/mo | ~$103K/mo |
| Stretch | $2.75M | $150K | $2.60M | 18 months | ~$153K/mo | ~$144K/mo |

Important interpretation: stretch does not automatically mean longer runway. It means faster capacity and broader evaluation/ASIC work while preserving the no-tape-out boundary.

## Monthly Cash Plan

The diligence workbook now includes an 18-month target cash-plan tab. It treats the target raise as $1.85M planned spend plus $150K reserve. This gives investors a concrete answer to burn/runway questions, while still preserving the caveat that hire timing, vendor spend, taxes, insurance, and benefits require CFO/accounting review.

## Dilution Sensitivity

Illustrative SAFE cap math before option pool, prior instruments, side letters, or priced-round mechanics:

| Post-money cap | $1.25M min | $2.0M target | $2.75M stretch |
| --- | --- | --- | --- |
| $8M | 15.6% | 25.0% | 34.4% |
| $10M | 12.5% | 20.0% | 27.5% |
| $12M | 10.4% | 16.7% | 22.9% |
| $15M | 8.3% | 13.3% | 18.3% |
| $18M | 6.9% | 11.1% | 15.3% |

This is sensitivity only, not a cap recommendation. Do not offer a cap in the room unless counsel/CFO has approved it.

# Financial Claims That Are Safe Friday

"We are raising a $2.0M target pre-seed, with a $1.25M minimum viable close and a $2.75M stretch plan."

"The target plan is roughly 18 months of runway."

"The round funds measured workload proof, IP/legal readiness, ASIC feasibility, demo reliability, and operations."

"The round does not fund tape-out."

"Reservation pricing is a qualification mechanism; material revenue requires scoped written work."

"Final SAFE terms, valuation cap, discount, pro-rata rights, and option pool mechanics require counsel/CFO review."

# Financial Claims To Avoid

Do not state a valuation cap unless approved.

Do not imply the $18.4M median seed pre-money benchmark is ATOMiK's valuation.

Do not forecast revenue before signed customer agreements or SOWs.

Do not imply public reservation prices are the full commercial model.

Do not claim customer traction, LOIs, or revenue without signed evidence.

Do not say pre-seed funds production silicon, tape-out, or volume manufacturing.

Do not model battery, heat, cooling, water, footprint, or power-bill savings as financial ROI until workload-specific measurement exists.

# Revenue Readiness

Current commercial stage:

| Stream | Current status | Financial treatment |
| --- | --- | --- |
| Proof review reservation | Public $750 reservation | Qualification signal only. |
| Technical evaluation reservation | Public $2,500 reservation | Scoping signal only; not material revenue. |
| Scoped design-partner evaluation | Request-based | First plausible material customer-funded proof path. Requires written SOW. |
| Sponsored proof work | Request-based | Possible near-term non-dilutive support if a partner has a painful workload. |
| Licensing/IP diligence | Future/request-based | Requires workload proof, IP packet, and integration path. |
| Commercial licensing / embedded IP | Future | Not forecastable yet. |

The financial model should not rely on reservations to underwrite the round. The investor case is that reservations and SOWs create market validation and proof artifacts, not near-term cash scale.

# Friday Financing Answer

Short version:

We are raising a $2.0M target pre-seed. The plan gives us roughly 18 months to produce measured customer workload proof, strengthen the IP packet, complete ASIC feasibility, and build a design-partner/licensing path. It does not fund tape-out.

If asked for valuation:

We are planning to use a SAFE structure, but I do not want to improvise the cap or terms. The final SAFE structure, valuation cap, discount, pro-rata rights, option-pool mechanics, and closing details should be finalized with counsel/CFO.

If asked why $2.0M:

The target is sized around the next evidence gates. Below that, the $1.25M plan keeps us focused on one measured workload path. Above that, the $2.75M stretch accelerates capacity and broader feasibility work. None of the plans turn into a tape-out budget.

# Diligence Gaps Before A Serious Follow-Up

Formal cap table after entity formation, stock issuance, any advisor grants, and prior obligations are verified.

Counsel-approved SAFE structure and terms.

Option-pool sizing and hiring plan.

Vendor-backed IP/legal budget.

ASIC mentor or advisor quote-backed feasibility budget.

Monthly cash plan by hire/contractor/vendor.

Paid-evaluation SOW template with pricing, deliverables, ownership, confidentiality, and success criteria.

Customer pipeline status with source, stage, next action, owner, and expected proof gate.

# Unmodeled / CFO Estimate Needed

These items are not currently modeled with CFO-level precision. Keep them visible in follow-up diligence:

Payroll taxes and benefits.

D&O, general liability, cyber, and other insurance.

Accounting, bookkeeping, tax, and investor-reporting support.

Delaware C-Corp conversion or formation costs.

Legal close costs, SAFE review, side letters, and cap-table setup.

IP prosecution variability and prior-art review.

FPGA/dev-board/tooling variability.

Cloud/dev infrastructure.

Travel and customer-evaluation support costs.

Contingency beyond the $150K reserve.

# Evaluation SOW Economics - Planning Only

Do not forecast this as revenue until a signed scope exists. A real evaluation SOW should price and define:

Workload intake.

Baseline mapping.

Success metric definition.

Test harness and artifact creation.

Readout and fit/no-fit recommendation.

Optional partner-funded proof work.

Pricing: TBD / scoped quote only.

Accounting treatment: not forecast until signed SOW.

# Recommendation

For Friday, use the financials as a milestone plan, not a forecast. The cleanest investor posture is disciplined:

We know exactly what the next dollar is supposed to prove, and we are not spending as if the proof is already complete.